## Sprint 1
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Committed hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Requirement clarification of web application with team | Savani | Product owner | 6 | 5 | 5 | 2 | 2 | 0 | 0
2 | Discussion of Product backlog items with Scrum master | Savani | Product owner | 2 | 2 | 0 | 0 | 0 | 0 | 0
3 | Verification of Product backlog items | Savani | Product owner | 1 | 1 | 1 | 1 | 0 | 0 | 0
4 | Preparation of product backlog | Savani | Scrum master | 2 | 2 | 2 | 2 | 2 | 0 | 0
5 | Requirement clarification for login screen | Savani | Scrum master | 1 | 1 | 1 | 0 | 0 | 0 | 0
6 | Discussion on test plane and test schedule with QA | Savani | Scrum master | 4 | 3 | 2 | 2 | 0 | 0 | 0
7 | Prepare test plans | Savani | QA | 3 | 3 | 3 | 2 | 2 | 0 | 0
8 | Prepare test schedules | Savani | QA | 2 | 2 | 2 | 2 | 0 | 0 | 0
9 | Prepare conceptual & logical designs of Database | Avishka | Database designer | 3 | 2 | 1 | 1 | 1 | 0 | 0
10 | Discussion of database design with scrum master | Avishka | Database designer | 1 | 1 | 1 | 0 | 0 | 0 | 0
11 | Develop the physical database for the prerared design | Avishka | Database designer | 2 | 2 | 0 | 0 | 0 | 0 | 0
12 | Login form back-end programming | Avishka | Programmer1 | 5 | 5 | 3 | 3 | 2 | 0 | 0
13 | Discussion of login process with database designer | Avishka | Programmer1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
14 | Setup database connectivity with login | Avishka | Programmer1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15 | Discussion of security features to be included in login with scrum master | Avishka | Programmer1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
16 | Discussion of security features to be included in login with database designer | Avishka | Programmer1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
17 | Implementing required security features on login | Avishka | Programmer1 | 2 | 2 | 2 | 0 | 0 | 0 | 0
18 | Login screen layout design | Avishka | Programmer1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
19 | Login screen UI design | Avishka | Programmer1 | 3 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Total (Hrs) | 42 | 36 | 24 | 16 | 9 | 0

## Sprint 2
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 2 | 2 | 2 | 0 | 0 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 1 | 1 | 1 | 1 | 1 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 2 | 2 | 0 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout of login screen | Savani | Scrum master | 1 | 1 | 1 | 1 | 0 | 0 | 0
6 | Discussion on test results and required changes of login with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 2 | 0 | 0
7 | Prepare test cases for test Student Home & Message App | Savani | QA | 2 | 2 | 2 | 0 | 0 | 0 | 0
8 | Test the Student Home & Message App using advocate test cases | Savani | QA | 5 | 5 | 5 | 3 | 3 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 2 | 0 | 0
10 | Design the table to Student Home & message app | Avishka | Database designer | 2 | 2 | 2 | 2 | 0 | 0 | 0
11 | Implement SQL functions related to Student Home & message app | Avishka | Database designer | 3 | 3 | 3 | 3 | 3 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
13 | Implement the UI design for Student Home | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
14 | Implement the UI design for Student Message App | Avishka | Programmer1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
15 | Backend code for Student home | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
16 | Backend code for Message app | Avishka | Programmer1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
17 | Testing the Student Home | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 2 | 0 | 0
18 | Testing the Student Message app | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  |  | Total (Hrs) | 42 | 40 | 29 | 22 | 13 | 0

## Sprint 3
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 1 | 1 | 1 | 1 | 1 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 2 | 0 | 0 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 2 | 2 | 0 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 2 | 2 | 1 | 1 | 0 | 0 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 2 | 0 | 0
7 | Prepare test cases for test Student Upload documents & Meeting page | Savani | QA | 2 | 2 | 2 | 0 | 0 | 0 | 0
8 | Test the Upload documents & Meeting page using advocate test cases | Savani | QA | 5 | 5 | 5 | 3 | 3 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 2 | 0 | 0
10 | Design the table to Upload documents & Meeting page | Avishka | Database designer | 2 | 2 | 2 | 2 | 0 | 0 | 0
11 | Implement SQL functions related toUpload documents & Meeting page | Avishka | Database designer | 3 | 3 | 3 | 3 | 3 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
13 | Implement the UI design for Upload documents | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
14 | Implement the UI design for Meeting page | Avishka | Programmer1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
15 | Backend code for Upload documents | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
16 | Backend code for Meeting page | Avishka | Programmer1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
17 | Testing the Upload documents | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 2 | 0 | 0
18 | Testing the Meeting page | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  |  |  | 42 | 40 | 28 | 21 | 12 | 0

## Sprint 4
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 3 | 3 | 3 | 2 | 1 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 2 | 2 | 2 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 1 | 1 | 0 | 0 | 0 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 2 | 2 | 0 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 1 | 1 | 1 | 1 | 1 | 0 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 0 | 0 | 0
7 | Prepare test cases for test Student Blogging | Savani | QA | 3 | 3 | 2 | 2 | 2 | 0 | 0
8 | Test the Blogging page using advocate test cases | Savani | QA | 4 | 4 | 4 | 3 | 2 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 0 | 0 | 0
10 | Design the table to Upload Blogging page | Avishka | Database designer | 3 | 3 | 2 | 1 | 0 | 0 | 0
11 | Implement SQL functions related toBlogging page | Avishka | Database designer | 5 | 5 | 4 | 3 | 1 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
13 | Implement the UI design for Blogging page | Avishka | Programmer1 | 4 | 4 | 3 | 1 | 0 | 0 | 0
14 | Backend code for Blogging page | Avishka | Programmer1 | 3 | 3 | 3 | 2 | 1 | 0 | 0
15 | Testing the Blogging page | Avishka | Programmer1 | 3 | 3 | 3 | 2 | 0 | 0 | 0
|  |  | Total (Hrs) | 42 | 41 | 34 | 23 | 10 | 0

## Sprint 5
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 2 | 0 | 0 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 2 | 2 | 0 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 2 | 0 | 0 | 0 | 0 | 0 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 2 | 0 | 0
7 | Prepare test cases for test Tutor page & Tutor message page | Savani | QA | 2 | 2 | 2 | 2 | 0 | 0 | 0
8 | Test the Tutor page & Tutor message page using advocate test cases | Savani | QA | 5 | 5 | 5 | 3 | 3 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 2 | 0 | 0
10 | Design the table toTutor page & Tutor message page | Avishka | Database designer | 2 | 2 | 2 | 2 | 0 | 0 | 0
11 | Implement SQL functions related to Tutor page & Tutor message page | Avishka | Database designer | 3 | 3 | 3 | 3 | 3 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
13 | Implement the UI design for Tutor Page | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
14 | Implement the UI design for Tutor Message page | Avishka | Programmer1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
15 | Backend code for Tutor Page | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
16 | Backend code for Tutor Message page | Avishka | Programmer1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
17 | Testing theTutor Page | Avishka | Programmer1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
18 | Testing the Tutor Message page | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  |  | Total (Hrs) | 43 | 38 | 25 | 20 | 10 | 0

## Sprint 6
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 2 | 2 | 0 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 2 | 1 | 0 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 3 | 3 | 2 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 2 | 1 | 1 | 1 | 1 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 0 | 0 | 0
7 | Prepare test cases for test tutor uploaded documents & tutor Meeting page | Savani | QA | 2 | 2 | 2 | 2 | 2 | 0 | 0
8 | tutor uploaded documents & tutor Meeting page using advocate test cases | Savani | QA | 5 | 5 | 5 | 3 | 0 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 1 | 1 | 1 | 0 | 0
10 | Design the table to tutor uploaded documents & tutor Meeting page | Avishka | Database designer | 2 | 2 | 2 | 2 | 0 | 0 | 0
11 | Implement SQL functions related to tutor uploaded documents & tutor Meeting page | Avishka | Database designer | 3 | 3 | 2 | 2 | 2 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
13 | Implement the UI design for Tutor Upload page | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0
14 | Implement the UI design for Tutor Meeting page | Avishka | Programmer1 | 2 | 0 | 0 | 0 | 0 | 0
15 | Backend code for Tutor Uploaded Page | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
16 | Backend code for Tutor Meeting page | Avishka | Programmer1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
17 | Testing the Tutor Uploaded Page | Avishka | Programmer1 | 2 | 2 | 0 | 0 | 0 | 0
18 | Testing the Tutor Meeting page | Avishka | Programmer1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  |  | Total (Hrs) | 43 | 39 | 27 | 20 | 6 | 0

## Sprint 7
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 3 | 3 | 3 | 2 | 1 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 2 | 2 | 2 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 1 | 1 | 0 | 0 | 0 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 2 | 2 | 0 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 1 | 1 | 1 | 1 | 1 | 0 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 0 | 0 | 0
7 | Prepare test cases for test Statictical Reports | Savani | QA | 3 | 3 | 2 | 2 | 2 | 0 | 0
8 | Test the Statictical Reports using advocate test cases | Savani | QA | 4 | 4 | 4 | 3 | 2 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 0 | 0 | 0
10 | Design the table toStatictical Reports | Avishka | Database designer | 3 | 3 | 2 | 1 | 0 | 0 | 0
11 | Implement SQL functions related to Statictical Reports | Avishka | Database designer | 5 | 5 | 4 | 3 | 1 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
13 | Implement the UI design for Statictical Reports | Avishka | Programmer1 | 4 | 4 | 3 | 1 | 0 | 0 | 0
14 | Backend code for Statictical Reports | Avishka | Programmer1 | 3 | 3 | 3 | 2 | 1 | 0 | 0
15 | Testing the Statictical Reports | Avishka | Programmer1 | 3 | 3 | 3 | 2 | 0 | 0 | 0
|  |  | Total (Hrs) | 42 | 41 | 34 | 23 | 10 | 0

## Sprint 8
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 1 | 1 | 1 | 1 | 1 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 1 | 0 | 0 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 3 | 2 | 1 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 2 | 2 | 1 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 4 | 2 | 2 | 0 | 0 | 0 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 2 | 0 | 0
7 | Prepare test cases for test Admin panel | Savani | QA | 3 | 3 | 2 | 2 | 1 | 0 | 0
8 | Test the Admin panel using advocate test cases | Savani | QA | 1 | 1 | 1 | 1 | 0 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 1 | 0 | 0
10 | Design the table to Admin panel | Avishka | Database designer | 3 | 3 | 2 | 1 | 0 | 0 | 0
11 | Implement SQL functions related to Admin panel | Avishka | Database designer | 5 | 5 | 4 | 3 | 1 | 0 | 0
12 | Fixing of bugs reported on test results | Avishka | Programmer1 | 3 | 3 | 1 | 0 | 0 | 0 | 0
13 | Implement the UI design for Admin panel | Avishka | Programmer1 | 4 | 4 | 3 | 1 | 0 | 0 | 0
14 | Backend code for Admin panel | Avishka | Programmer1 | 3 | 3 | 3 | 2 | 1 | 0 | 0
15 | Testing the Admin panel | Avishka | UI designer | 3 | 3 | 3 | 2 | 0 | 0 | 0
|  |  | Total (Hrs) | 42 | 39 | 32 | 20 | 8 | 0

## Sprint 9
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 1 | 1 | 1 | 1 | 1 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 1 | 0 | 0 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 3 | 2 | 1 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 2 | 2 | 1 | 0 | 0 | 0
5 | Discussion and finalizing the features and layout | Savani | Scrum master | 4 | 2 | 2 | 0 | 0 | 0 | 0
6 | Discussion on test results and required changes with developers & QA | Savani | Scrum master | 2 | 2 | 2 | 2 | 2 | 0 | 0
7 | Prepare test cases for test the all system | Savani | QA | 3 | 3 | 2 | 2 | 1 | 0 | 0
8 | Test the System using advocate test cases | Savani | QA | 1 | 1 | 1 | 1 | 0 | 0 | 0
9 | Documenting test results | Savani | QA | 2 | 2 | 2 | 2 | 1 | 0 | 0
10 | Fixing of bugs reported on last sprint | Avishka | Programmer1 | 4 | 4 | 3 | 2 | 0 | 0 | 0
11 | Finalaize the UI designs in the system | Avishka | Programmer1 | 5 | 5 | 3 | 3 | 2 | 0 | 0
12 | Finalaize the backend code for the system | Avishka | Programmer1 | 4 | 4 | 4 | 2 | 2 | 0 | 0
13 | Finalaize the database in the system | Avishka | Database designer | 5 | 5 | 3 | 3 | 2 | 0 | 0
14 | Implement the database backup system | Avishka | Database designer | 3 | 3 | 3 | 2 | 2 | 0 | 0
|  |  | Total (Hrs) | 42 | 39 | 32 | 23 | 14 | 0

## Sprint 10
Task No | Description | Name | Role |  | Remaining hours as end of |  |  |  |  | Remaining hours
|  |  |  | Allocated hours | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
1 | Verification of sprint backlogs | Savani | Product owner | 2 | 1 | 1 | 1 | 1 | 0 | 0
2 | Verification of test results with QA | Savani | Product owner | 2 | 2 | 1 | 0 | 0 | 0 | 0
3 | Discussion on findings of test results with Scrum master | Savani | Product owner | 3 | 3 | 3 | 2 | 1 | 0 | 0
4 | Preparation of sprint backlog | Savani | Scrum master | 3 | 2 | 2 | 1 | 0 | 0 | 0
5 | Discussion and finalizing the System | Savani | Scrum master | 4 | 2 | 2 | 0 | 0 | 0 | 0
6 | Discussion on implemention | Savani | Scrum master | 3 | 2 | 2 | 2 | 2 | 0 | 0
7 | Documenting the user manual | Savani | Scrum master | 4 | 3 | 2 | 2 | 1 | 0 | 0
10 | implement the database | Avishka | Database designer | 6 | 6 | 4 | 2 | 0 | 0 | 0
11 | implement the system | Avishka | Programmer1 | 7 | 7 | 6 | 5 | 3 | 0 | 0
12 | implement a backup method | Avishka | Database designer | 3 | 3 | 1 | 0 | 0 | 0 | 0
13 | Finalaize the system | Avishka | Programmer1 | 5 | 4 | 3 | 1 | 0 | 0 | 0
|  |  | Total (Hrs) | 42 | 35 | 27 | 16 | 8 | 0